## Work Breakdown Structure (WBS)
FFPr Work Breakdown Structure (WBS) template
Yes
In Progress
No
ID | Activity Level 1 | Year 1 | Activity Level 2 | Activity Level 3 | Work Package | Start Date | End Date | Duration | Completion | Organization | Assignment
Administration (to be filled in according to hierarchy below)
1 | Administration
2 | Monetization
3 | Monitoring and Evaluation, Reporting
Activities
4 | [Activity Level 1]
4.1 |  | [Year]
4.1.1 |  |  | [Activity Level 2]
4.1.1.1 |  |  |  | [Activity Level 3]
4.1.1.1.1 |  |  |  |  | [Work Package]
5 | Example: Infrastructure: Feeder and Connecter Roads
5.1 |  | Year 1
5.1.1 |  |  | Road # 21 Baconding – Bindaba 5.6km |  |  | 2019-08-01 | 2019-09-15 | 32
5.1.1.1 |  |  |  | Approvals |  | 2019-08-01 | 2019-08-27 | 19
5.1.1.1.1 |  |  |  |  | Authorities Agreement | 2019-08-01 | 2019-08-07 | 5 | In Progress | [Prime Recipient] | Niru Pradhan
5.1.1.1.2 |  |  |  |  | Signature of the protocol for the road maintenance (Mayor or Prefect) | 2019-08-07 | 2019-08-09 | 3 | Yes | [Sub-Recipient 1] | William Shields
5.1.1.1.3 |  |  |  |  | Mining Services and Geology Authorization | 2019-08-07 | 2019-08-20 | 10 | In Progress | [Sub-Recipient 2] | Kameron Burt
5.1.1.1.4 |  |  |  |  | Meet with regional labor inspector for CFW registration and Meet with the Mayor of the road concerned | 2019-08-10 | 2019-08-10 | 0 | In Progress
5.1.1.1.5 |  |  |  |  | Visit the field with the concerned village leaders and Consensus around the itinerary | 2019-08-01 | 2019-08-25 | 17 | No |  | Rebecca Coggins
5.1.1.1.6 |  |  |  |  | Communicate on the Recruiting process CFW | 2019-08-01 | 2019-08-27 | 19 |  | [Sub-Recipient 3] | Susan Waage
5.1.1.2 |  |  |  | Topographical survery |  | 2019-09-01 | 2019-09-15 | 10 |  |  | Nicola Sakhleh
5.1.1.2.1 |  |  |  |  | Analyze the existing condition of the road | 2019-09-01 | 2019-09-15 | 10
5.1.1.2.2 |  |  |  |  | Implant the topographic boundary marker | 2019-09-15 | 2019-09-18 | 3 |  | [Sub-Recipient 1]
5.1.1.2.3 |  |  |  |  | Transfer the data and Project Design project to the computer | 2019-09-20 | 2019-09-21 | 1
5.1.1.2.4 |  |  |  |  | Implement the axis of the road and designing | 2019-09-22 | 2019-09-15 | -5
5.2 |  | Year 2
5.2.1 |  |  | Road # 21 Baconding – Bindaba 5.6km
5.2.1.1 |  |  |  | Bush clearing |  | 2019-10-01 | 2019-11-05 | 26
5.2.1.1.1 |  |  |  |  | Deploy teams and provide equipment | 2019-10-01 | 2019-10-04 | 4
5.2.1.1.2 |  |  |  |  | Weed and stump removal | 2019-10-04 | 2019-11-03 | 21
5.2.1.1.3 |  |  |  |  | Cut down the trees on the right-of-way | 2019-10-04 | 2019-10-30 | 19
5.2.1.1.4 |  |  |  |  | Clear the trunks from the right away | 2019-10-30 | 2019-11-05 | 5
Formulas:
Duration = NETWORKDAYS([Start Date],[End Date])

## WBS Dictionary
ID | Work Package | Description of work | Responsible Party (drop-down) | Deliverables | Est. Contribution to Project Targets | Actual Contribution to Project Targets | Resources required | Necessary Procurements
Match to ID in WBS | Name of Work Package | Explain what this package is about, and the statement of work of this work package. What work has to be performed or delivered as part of this work package. | If prime recipient's responsibility, what staff member is tasked with completion. If sub-recipient responsibility, indicate as such | What outputs are necessary for the work package to be considered achieved (ie. MOU signed, # of beneficiaries trained)? | if applicable |  | What project resources are required for this activity (vehicles, etc.) | Are any procurements necessary to complete work package?

## Gantt Chart
FFPr Gantt Chart Template
Agreement #: |  |  | Agricultural Schedule Legend
Country: |  |  | Planting, Stocking, Input Procurement
PVO: |  |  | Grow-out
Duration: |  |  | Harvesting
Yes
In Progress
No
Note: Only edit cells in columns A:F | [6 empty] | Year 1 | [52 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
Agricultural Schedule
ID | Work Package | Start | End | Duration | Completed? | Days Past Due | time axis 2018-10-01 to 2023-09-01
5.1.1.1.1 | Authorities Agreement | 2018-10-01 | 2018-10-07 | 5 | In Progress | 17
5.1.1.1.2 | Signature of the protocol for the road maintenance (Mayor or Prefect) | 2018-10-07 | 2018-10-22 | 11 | Yes | -
5.1.1.1.3 | Mining Services and Geology Authorization | 2018-10-07 | 2018-11-18 | 30 | In Progress | -14
5.1.1.1.4 | Meet with regional labor inspector for CFW registration and Meet with the Mayor of the road concerned | 2018-10-10 | 2018-10-25 | 12 | In Progress | 4
5.1.1.1.5 | Visit the field with the concerned village leaders and Consensus around the itinerary | 2018-10-01 | 2018-10-26 | 20 | No | 3
5.1.1.1.6 | Communicate on the Recruiting process CFW | 2018-10-01 | 2018-10-27 | 20 | 0 | 2

## Staffing Dictionary
Organization
[Prime Recipient]
[Sub-Recipient 1]
[Sub-Recipient 2]
[Sub-Recipient 3]
Staff | Organization (drop-down) | Position
Niru Pradhan
Susan Waage
Kameron Burt
Nicola Sakhleh
Irina Gonzales
Rebecca Coggins
William Shields
Waleed Rabieh

## Agricultural Schedule
Agricultural Schedule (fill schedule for as many planting seasons the project is projected to cover)
Note: Do not use the same End and Start date. If Grow Out Period ends on 1/1/2019, for instance, Harvesting must begin on 1/2/2019
Period | Planting, Stocking, Input Procurement |  | Grow out Period |  | Harvesting
| Start | End | Start | End | Start | End
1 | 2018-10-03 | 2018-10-29 | 2018-11-01 | 2018-12-18 | 2018-12-18 | 2019-01-20
2 | 2019-04-03 | 2019-04-16 | 2019-11-01 | 2019-12-18
3
4
5
6
7
8
9
10